## Overview
Weekly Status Report
Summary
Total Projects
Active Tasks
Completed Tasks
Total Deliverables
Project Overview
Project | Category | Status | Priority | Tasks | Completed | Allocated (hrs) | Spent (hrs)
Time Overview
[6 empty] | Allocated | Spent
TOTAL

## Projects
Project ID | Title | Category | Supervisor | Site | Description | Status | Priority | Start Date | End Date | Deadline | Date Completed | Notes
P-001 | Wiring Harness Design & Documentation | Ongoing |  |  | Complete all design schematics, wiring diagrams, legends, and technical documentation for the FSAE wiring harness. | In Progress |  | 2025-11-01 | 2026-03-30 | 2026-04-10
P-002 | Wiring Harness Construction | Ongoing |  |  | Physical build of the FSAE wiring harness — from form board through final sealed assembly. | In Progress |  | 2026-01-15 |  | 2026-04-10
P-003 | Harness Cost Report | Ongoing |  |  | FSAE cost report for the wiring harness — assembly structure, part numbers, BOM, and pricing. | Not Started |  | 2026-03-23 |  | 2026-04-10
P-004 | Harness Design Brief | Weekly |  |  | 6-slide presentation outlining all key design decisions for the FSAE wiring harness. | Not Started |  | 2026-04-11 |  | 2026-05-17
P-005 | Harness Design Binder | Weekly |  |  | Compile all harness documentation — schematics, diagrams, legends, cost report, design brief, test records — into a single design binder. | Not Started |  | 2026-05-18 |  | 2026-06-01

## Tasks
Task ID | Project ID | Title | Description | Supervisor | Site | Status | Priority | Start Date | End Date | Deadline | Status Commentary | Date Completed
T-001 | P-001 | Harness Schematic Design | Create the full electrical schematic for the wiring harness including all circuits, power distribution, and grounding. |  | UA | Completed | 1 | 2025-11-01 | 2026-01-15 | 2026-01-15 | Schematic design phase complete. All circuits defined. | 2026-01-15
T-002 | P-001 | Wiring Diagrams & Legends | Produce detailed wiring diagrams and legend documentation for all harness circuits and connectors. |  | UA | In Progress | 2 | 2025-12-01 |  | 2026-03-30 | Currently working through documentation. Diagrams and legends in progress. |  | 2026-03-24
T-003 | P-002 | Harness Shape & Form Board | Build the harness jig/form board and lay out primary wire routing paths. |  | UA | Completed | 1 | 2026-01-15 | 2026-02-28 | 2026-02-28 | Form board built. Harness shape established. | 2026-02-28
T-004 | P-002 | Shutdown Circuit (SDC) Installation | Route, wire, and integrate the mandatory FSAE shutdown circuit into the harness. |  | UA | Not Started | 1 | 2026-03-23 |  | 2026-04-01 |  |  | 2026-03-24
T-005 | P-002 | Pin & Label All Wires | Crimp pins/terminals on every wire end and apply identification labels. |  | UA | Not Started | 2 | 2026-03-25 |  | 2026-04-03 |  |  | 2026-03-26
T-006 | P-002 | Connector Installation | Insert pinned wires into all connectors and verify seating and retention. |  | UA | Not Started | 2 | 2026-04-01 |  | 2026-04-05 |  |  | 2026-03-28
T-007 | P-002 | Taping, Sheathing & Sealing | Complete harness finish work — bundling, protection, and environmental sealing. |  | UA | Not Started | 2 | 2026-04-05 |  | 2026-04-10 |  |  | 2026-03-29
T-008 | P-003 | Assembly Structure & Part Numbers | Define the assembly hierarchy and assign FSAE-compliant part numbers to every component. |  | UA | Not Started | 2 | 2026-03-23 |  | 2026-03-30 |  |  | 2026-03-25
T-009 | P-003 | Parts Itemization | Catalog every harness component with specifications, lengths, and quantities. |  | UA | Not Started | 2 | 2026-03-28 |  | 2026-04-05 |  |  | 2026-03-27
T-010 | P-003 | Cost Report Compilation & Submission | Source pricing, calculate totals, format to FSAE template, and submit. |  | UA | Not Started | 1 | 2026-04-03 |  | 2026-04-10 |  |  | 2026-03-25
T-011 | P-004 | Design Brief Content Development | Research, outline, and draft all 6 slides for the harness design brief. |  | UA | Not Started | 2 | 2026-04-11 |  | 2026-05-07 |  |  | 2026-03-30
T-012 | P-004 | Design Brief Review & Submission | Internal review, incorporate feedback, and submit the final design brief. |  | UA | Not Started | 3 | 2026-05-07 |  | 2026-05-17 |  |  | 2026-03-24
T-013 | P-005 | Design Binder Compilation | Gather, organize, and compile all harness documentation into a single binder. |  | UA | Not Started | 3 | 2026-05-18 |  | 2026-05-28 |  |  | 2026-03-25
T-014 | P-005 | Final Binder Review & Submission | Review the compiled binder for completeness, format, and submit. |  | UA | Not Started | 3 | 2026-05-28 |  | 2026-06-01 |  |  | 2026-03-26

## Deliverables
Deliverable ID | Task ID | Title | Description | Status | Start Date | End Date | Deadline | % Complete
D-001 | T-001 | Define all electrical circuits and loads | Identify every circuit on the car: power, signal, sensor, actuator. | Completed | 2025-11-01 | 2025-12-01 | 2025-12-01 | 100
D-002 | T-001 | Create full electrical schematic | Draw complete wiring schematic showing all connections, fuses, relays, and ECU pinouts. | Completed | 2025-12-01 | 2025-12-20 | 2025-12-20 | 100
D-003 | T-001 | Define wire gauges and types per circuit | Select appropriate wire gauge, insulation type, and color for each circuit based on current draw. | Completed | 2025-12-15 | 2026-01-10 | 2026-01-10 | 100
D-004 | T-001 | Finalize harness routing layout | Define physical routing paths on the chassis for every branch of the harness. | Completed | 2026-01-05 | 2026-01-15 | 2026-01-15 | 100
D-005 | T-002 | Complete circuit wiring diagrams | Draw per-circuit wiring diagrams with pin assignments, wire colors, and routing notes. | In Progress | 2025-12-01 |  | 2026-02-28 | 70
D-006 | T-002 | Create wire color code legend | Document the color coding scheme for every wire function and circuit type. | In Progress | 2026-01-15 |  | 2026-03-10 | 50
D-007 | T-002 | Document connector pinout tables | Create pinout reference tables for every connector on the harness. | In Progress | 2026-02-01 |  | 2026-03-20 | 30
D-008 | T-002 | Create harness assembly drawing | Produce a dimensioned assembly drawing showing all branches, breakouts, and connector positions. | In Progress | 2026-02-15 |  | 2026-03-30 | 40
D-009 | T-003 | Build harness jig / form board | Construct the physical board with standoffs matching chassis routing. | Completed | 2026-01-15 | 2026-02-15 | 2026-02-15 | 100
D-010 | T-003 | Route primary wire paths on form board | Lay wires along defined paths, establish branch points and breakouts. | Completed | 2026-02-10 | 2026-02-28 | 2026-02-28 | 100
D-011 | T-003 | Cut wires to length | Measure and cut all wires with service-loop allowance per the routing layout. | Completed | 2026-02-20 | 2026-02-28 | 2026-02-28 | 100
D-012 | T-004 | Source and verify SDC components | Confirm all SDC switches, relays, and interlocks are on hand and to spec. | Not Started | 2026-03-23 |  | 2026-03-25 | 0
D-013 | T-004 | Route SDC wiring through harness | Run SDC loop wiring along defined path, maintaining isolation from signal wires. | Not Started | 2026-03-25 |  | 2026-03-28 | 0
D-014 | T-004 | Integrate SDC into harness and test loop continuity | Connect SDC inline with harness, verify the full loop opens/closes correctly. | Not Started | 2026-03-28 |  | 2026-04-01 | 0
D-015 | T-005 | Crimp pins and terminals on all wire ends | Crimp correct pin/terminal for each connector type onto every wire. | Not Started | 2026-03-25 |  | 2026-03-30 | 0
D-016 | T-005 | Apply wire labels and heat-shrink IDs | Label every wire at both ends with circuit ID using printed heat-shrink or flag labels. | Not Started | 2026-03-28 |  | 2026-04-01 | 0
D-017 | T-005 | Continuity check on all pinned wires | Verify end-to-end continuity on every crimped and labeled wire. | Not Started | 2026-04-01 |  | 2026-04-03 | 0
D-018 | T-006 | Install inline connectors | Insert pins into inline connector housings per pinout tables. | Not Started | 2026-04-01 |  | 2026-04-03 | 0
D-019 | T-006 | Install bulkhead and panel-mount connectors | Populate and secure all panel-mount and bulkhead connectors. | Not Started | 2026-04-02 |  | 2026-04-04 | 0
D-020 | T-006 | Verify connector seating and pin retention | Tug-test every pin, confirm TPA clips engaged, and check for backed-out pins. | Not Started | 2026-04-04 |  | 2026-04-05 | 0
D-021 | T-007 | Tape wire bundles at branch points | Spot-tape and spiral-wrap all branch junctions to secure wire groupings. | Not Started | 2026-04-05 |  | 2026-04-06 | 0
D-022 | T-007 | Apply protective sheathing and loom | Slide braided loom or split conduit over all harness trunks and branches. | Not Started | 2026-04-06 |  | 2026-04-07 | 0
D-023 | T-007 | Seal harness endpoints and grommets | Apply heat-shrink boots, grommets, and sealant at all harness pass-throughs. | Not Started | 2026-04-07 |  | 2026-04-09 | 0
D-024 | T-007 | Final harness QC inspection | Full visual and electrical inspection — continuity, insulation resistance, label check. | Not Started | 2026-04-09 |  | 2026-04-10 | 0
D-025 | T-008 | Define assembly hierarchy | Break the harness into logical assemblies and sub-assemblies (e.g. front loom, rear loom, engine loom, SDC loop). | Not Started | 2026-03-23 |  | 2026-03-25 | 0
D-026 | T-008 | Create part numbering scheme | Establish a consistent part numbering convention that satisfies FSAE cost report rules. | Not Started | 2026-03-24 |  | 2026-03-26 | 0
D-027 | T-008 | Assign part numbers to all components | Apply part numbers to every wire, connector, terminal, relay, fuse, and consumable. | Not Started | 2026-03-26 |  | 2026-03-30 | 0
D-028 | T-009 | Itemize all wires — gauge, color, length, quantity | List every wire run with its gauge, insulation color, measured length, and quantity. | Not Started | 2026-03-28 |  | 2026-04-01 | 0
D-029 | T-009 | Itemize connectors, pins, and terminals | List every connector housing, pin, socket, seal, and TPA clip with quantity per connector. | Not Started | 2026-03-30 |  | 2026-04-02 | 0
D-030 | T-009 | Itemize consumables — tape, sheathing, heat-shrink, seals | Catalog all consumable materials used in harness finishing with lengths/quantities. | Not Started | 2026-04-01 |  | 2026-04-03 | 0
D-031 | T-009 | Itemize relays, fuses, and miscellaneous electrical components | List all relays, fuse holders, fuses, grounding hardware, and mounting brackets. | Not Started | 2026-04-03 |  | 2026-04-05 | 0
D-032 | T-010 | Source pricing for all line items | Obtain unit pricing from suppliers or FSAE standard cost tables for every part. | Not Started | 2026-04-03 |  | 2026-04-06 | 0
D-033 | T-010 | Calculate total BOM cost by assembly | Sum extended costs per assembly and compute harness total. | Not Started | 2026-04-06 |  | 2026-04-08 | 0
D-034 | T-010 | Format cost report per FSAE template | Enter all data into the official FSAE cost report spreadsheet template. | Not Started | 2026-04-07 |  | 2026-04-09 | 0
D-035 | T-010 | Review and submit cost report | Final cross-check against BOM, resolve discrepancies, and submit. | Not Started | 2026-04-09 |  | 2026-04-10 | 0
D-036 | T-011 | Outline slide content and presentation structure | Define the narrative flow and key talking points for all 6 slides. | Not Started | 2026-04-11 |  | 2026-04-14 | 0
D-037 | T-011 | Slide 1 — Design requirements and constraints | Cover FSAE rules, vehicle electrical requirements, weight/packaging constraints. | Not Started | 2026-04-14 |  | 2026-04-18 | 0
D-038 | T-011 | Slide 2 — Harness architecture and topology | Present the overall harness topology: star vs. bus, branch strategy, node locations. | Not Started | 2026-04-18 |  | 2026-04-22 | 0
D-039 | T-011 | Slide 3 — Wire gauge and connector selection rationale | Justify gauge sizing, connector family choices, and contact ratings. | Not Started | 2026-04-22 |  | 2026-04-26 | 0
D-040 | T-011 | Slide 4 — Routing, packaging, and weight optimization | Explain physical routing decisions, weight trade-offs, and serviceability considerations. | Not Started | 2026-04-26 |  | 2026-04-30 | 0
D-041 | T-011 | Slide 5 — Safety systems and SDC integration | Detail SDC loop design, fail-safe philosophy, and rules compliance. | Not Started | 2026-04-30 |  | 2026-05-03 | 0
D-042 | T-011 | Slide 6 — Validation, testing, and lessons learned | Summarize test plan, validation results, and design iteration takeaways. | Not Started | 2026-05-03 |  | 2026-05-07 | 0
D-043 | T-012 | Internal team review of design brief | Circulate draft to team leads for feedback. | Not Started | 2026-05-07 |  | 2026-05-10 | 0
D-044 | T-012 | Incorporate feedback and finalize slides | Revise content and visuals based on review comments. | Not Started | 2026-05-10 |  | 2026-05-14 | 0
D-045 | T-012 | Submit design brief | Final export and submission of the 6-slide design brief. | Not Started | 2026-05-14 |  | 2026-05-17 | 0
D-046 | T-013 | Compile all wiring schematics and diagrams | Collect final versions of all schematics and wiring diagrams into the binder. | Not Started | 2026-05-18 |  | 2026-05-20 | 0
D-047 | T-013 | Include wire legends and connector pinout documentation | Insert color code legend, pinout tables, and wire schedule. | Not Started | 2026-05-19 |  | 2026-05-21 | 0
D-048 | T-013 | Insert cost report | Add the completed harness cost report section. | Not Started | 2026-05-20 |  | 2026-05-22 | 0
D-049 | T-013 | Insert design brief | Add the 6-slide design brief or its expanded narrative form. | Not Started | 2026-05-21 |  | 2026-05-23 | 0
D-050 | T-013 | Add construction photos and process notes | Document the build process with photos, notes on techniques, and assembly order. | Not Started | 2026-05-22 |  | 2026-05-25 | 0
D-051 | T-013 | Compile test and validation records | Include continuity test logs, insulation resistance results, and any inspection checklists. | Not Started | 2026-05-25 |  | 2026-05-28 | 0
D-052 | T-014 | Review binder for completeness and consistency | Cross-check all sections against a checklist; ensure no missing documents. | Not Started | 2026-05-28 |  | 2026-05-30 | 0
D-053 | T-014 | Format, bind, and print final document | Final formatting pass, print, and physically bind the design binder. | Not Started | 2026-05-29 |  | 2026-05-31 | 0
D-054 | T-014 | Submit design binder | Deliver the completed design binder. | Not Started | 2026-05-31 |  | 2026-06-01 | 0

## Timelines
Item ID | Item Type | Title | Parent ID | Start Date | Duration (days) | End Date | Deadline | Status | % Complete | Time Allocated | Time Spent | Scheduled Date | Milestones
P-001 | Project
P-002 | Project
P-003 | Project
P-004 | Project
P-005 | Project
T-001 | Task
T-002 | Task
T-003 | Task
T-004 | Task
T-005 | Task
T-006 | Task
T-007 | Task
T-008 | Task
T-009 | Task
T-010 | Task
T-011 | Task
T-012 | Task
T-013 | Task
T-014 | Task
D-001 | Deliverable
D-002 | Deliverable
D-003 | Deliverable
D-004 | Deliverable
D-005 | Deliverable
D-006 | Deliverable
D-007 | Deliverable
D-008 | Deliverable
D-009 | Deliverable
D-010 | Deliverable
D-011 | Deliverable
D-012 | Deliverable
D-013 | Deliverable
D-014 | Deliverable
D-015 | Deliverable
D-016 | Deliverable
D-017 | Deliverable
D-018 | Deliverable
D-019 | Deliverable
D-020 | Deliverable
D-021 | Deliverable
D-022 | Deliverable
D-023 | Deliverable
D-024 | Deliverable
D-025 | Deliverable
D-026 | Deliverable
D-027 | Deliverable
D-028 | Deliverable
D-029 | Deliverable
D-030 | Deliverable
D-031 | Deliverable
D-032 | Deliverable
D-033 | Deliverable
D-034 | Deliverable
D-035 | Deliverable
D-036 | Deliverable
D-037 | Deliverable
D-038 | Deliverable
D-039 | Deliverable
D-040 | Deliverable
D-041 | Deliverable
D-042 | Deliverable
D-043 | Deliverable
D-044 | Deliverable
D-045 | Deliverable
D-046 | Deliverable
D-047 | Deliverable
D-048 | Deliverable
D-049 | Deliverable
D-050 | Deliverable
D-051 | Deliverable
D-052 | Deliverable
D-053 | Deliverable
D-054 | Deliverable

## Gantt Chart
Item ID | Title | Start | End | Status | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02 | 2026-06-09
P-001
P-002
P-003
P-004
P-005
T-001
T-002
T-003
T-004
T-005
T-006
T-007
T-008
T-009
T-010
T-011
T-012
T-013
T-014
D-001
D-002
D-003
D-004
D-005
D-006
D-007
D-008
D-009
D-010
D-011
D-012
D-013
D-014
D-015
D-016
D-017
D-018
D-019
D-020
D-021
D-022
D-023
D-024
D-025
D-026
D-027
D-028
D-029
D-030
D-031
D-032
D-033
D-034
D-035
D-036
D-037
D-038
D-039
D-040
D-041
D-042
D-043
D-044
D-045
D-046
D-047
D-048
D-049
D-050
D-051
D-052
D-053
D-054