## Overview
Weekly Dashboard — March 25, 2026
Ashwin Conrad ¦ Engineering Co-op Student ¦ AltaGas Ltd.
Project Status Summary
Project | Category | Status | Priority | Active Tasks | % Complete | Allocated (hrs) | Spent (hrs)
Safety Critical Element (SCE) Identification | Weekly | In Progress | P1 – Urgent | 3 | 9/21 | — | —
Brazed Aluminum Heat Exchanger (BAHX) Study | Weekly | In Progress | P1 – Urgent | 4 | 7/19 | — | —
Corrosion Coupon Dashboard | Ongoing | In Progress | P2 – High | 2 | 4/13 | — | —
Inspection Scope Tool | Ongoing | In Progress | P2 – High | 1 | 4/8 | — | —
PI Vision Screen Cleanup | Ongoing | Ongoing | P5 – Background | 1 | 0/3 | — | —
AI & Python Workflow Automation | Ongoing | Ongoing | P5 – Background | 1 | 0/3 | — | —
Weekly Schedule
Priority | Wed 03/25 | Thu 03/26 | Fri 03/27 | Sat 03/28 | Sun 03/29 | Mon 03/30 | Tue 03/31
P1 – Urgent | SCE Identification - Harmattan & EEEP | BAHX Final Report
P2 – High | Maximo Tag Matching | BAHX Vendor Meeting - April 1 | BAHX Presentation | SCE Site Review Meetings | Auto-Triggered Email Data Pipeline
P3 – Medium | BAHX SOP Review | Inspection Scope Tool - Handoff Documentation | Corrosion Dashboard Handoff Documentation
P4 – Low
P5 – Background | AI & Python Applications - Exploration & Prototyping | PI Vision Screen Cleanup - Units, Tags, and Navigation
Time Overview
Project | Allocated (hrs) | Spent (hrs) | Remaining (hrs) | Utilization %
Safety Critical Element (SCE) Identification | — | — | — | —
Brazed Aluminum Heat Exchanger (BAHX) Study | — | — | — | —
Corrosion Coupon Dashboard | — | — | — | —
Inspection Scope Tool | — | — | — | —
PI Vision Screen Cleanup | — | — | — | —
AI & Python Workflow Automation | — | — | — | —
TOTAL | — | — | — | —
Upcoming Deadlines (Next 14 Days)
Deadline | Item | Status | Parent
2026-03-25 | Complete SCE identification for Harmattan | In Progress | SCE Identification - Harmattan & EEEP
2026-03-25 | Investigate and resolve unmatched tags (~55% remaining) | In Progress | Maximo Tag Matching
2026-03-25 | Outline presentation structure and key messages | In Progress | BAHX Presentation
2026-03-28 | Draft report - recommendations and action plan | In Progress | BAHX Final Report
2026-03-28 | Prepare BAHX unit specs and questions for vendor | In Progress | BAHX Vendor Meeting - April 1
2026-03-31 | SCE Identification - Harmattan & EEEP | In Progress | Safety Critical Element (SCE) Identification
2026-03-31 | Complete SCE identification for EEEP | In Progress | SCE Identification - Harmattan & EEEP
2026-03-31 | Maximo Tag Matching | In Progress | Safety Critical Element (SCE) Identification
2026-03-31 | Produce final Maximo match report with gap summary | Not Started | Maximo Tag Matching
2026-04-01 | BAHX Vendor Meeting - April 1 | In Progress | Brazed Aluminum Heat Exchanger (BAHX) Study
2026-04-01 | Attend vendor meeting and capture notes | Not Started | BAHX Vendor Meeting - April 1
2026-04-04 | Summarize vendor data into cost/lead-time table | Not Started | BAHX Vendor Meeting - April 1
2026-04-05 | Review SOPs for BAHX-related comments and restrictions | Not Started | BAHX SOP Review
2026-04-07 | Incorporate vendor cost and lead-time data (post Apr 1 meeting) | Not Started | BAHX Final Report
2026-04-07 | Write technical documentation - code architecture and logic | Not Started | Inspection Scope Tool - Handoff Documentation

## Projects
Project ID | Title | Category | Supervisor | Site | Description | Status | Priority | Start Date | End Date | Deadline | Date Completed | Notes
P-001 | Safety Critical Element (SCE) Identification | Weekly |  |  | Identify and catalog Safety Critical Elements across all AltaGas facilities by cross-referencing P&IDs, SDKs, and Maximo asset databases. | In Progress | 0 | 2025-02-01 |  | 2026-03-31
P-002 | Brazed Aluminum Heat Exchanger (BAHX) Study | Weekly |  |  | Technical study evaluating the condition, risk profile, and replacement strategy for BAHX units across AltaGas facilities. | In Progress | 0 | 2025-11-01 |  | 2026-05-15
P-003 | Corrosion Coupon Dashboard | Ongoing |  |  | Power BI dashboard tracking corrosion coupon data across all AltaGas facilities. | In Progress | 0 | 2025-09-01 |  | 2026-08-31
P-004 | Inspection Scope Tool | Ongoing |  |  | Python tool that assists with the creation of inspection scopes. Tool is complete and deployed; handoff documentation required. | In Progress | 0 | 2025-06-01 |  | 2026-04-30
P-005 | PI Vision Screen Cleanup | Ongoing |  |  | Long-term, background cleanup effort to improve PI Vision usability and pave the way for enterprise-wide PI screen standardization. | Ongoing | 0
P-006 | AI & Python Workflow Automation | Ongoing |  |  | Self-directed initiative exploring AI and Python tools for engineering workflow automation and operational optimization. | Ongoing | 0

## Tasks
Task ID | Project ID | Title | Description | Supervisor | Site | Status | Priority | Start Date | End Date | Deadline | Status Commentary | Date Completed
T-001 | P-001 | SCE Identification - Completed Facilities | Facilities where P&IDs are well-documented in SDKs and SCE identification has been completed. | Kurt MacKay | Multiple | Completed | 1 | 2025-02-01 | 2026-02-28 | 2026-02-28 | Majority of facilities completed. P&IDs were available in SDKs for these sites. | 2026-02-28
T-002 | P-001 | SCE Identification - Harmattan & EEEP | Harmattan and EEEP SDKs do not outline P&IDs for each tag, requiring alternative approaches to identify SCEs. | Kurt MacKay | Harmattan / EEEP | In Progress | 1 | 2026-01-15 |  | 2026-03-31 | SDKs for Harmattan and EEEP lack P&ID references per tag. Attempting alternative tag-to-SCE mapping approaches. |  | 2026-03-25
T-003 | P-001 | Maximo Tag Matching | Cross-reference identified SCE tags against the Maximo asset management database to validate equipment records. | Kurt MacKay | All | In Progress | 2 | 2025-10-01 |  | 2026-03-31 | Currently matching approximately 45% of tags to Maximo. Discrepancies in naming conventions and missing assets are the main blockers. |  | 2026-03-25
T-004 | P-001 | SCE - On-Hold Facilities (PSGP-1 Dimsdale & Townsend) | SCE work paused for PSGP-1 Dimsdale and Townsend pending completion of their SDK validation processes. | Kurt MacKay | PSGP-1 Dimsdale / Townsend | On Hold | 4 | 2025-06-01 |  | 2026-06-30 | Both facilities are currently undergoing SDK validation. SCE identification will resume once validated SDKs are available.
T-005 | P-001 | SCE Site Review Meetings | Present SCE findings to each facility site team and discuss action items. | Kurt MacKay | All | Not Started | 2 | 2026-04-01 |  | 2026-06-30 | Target: complete site discussions by end of June. |  | 2026-03-28
T-006 | P-002 | BAHX Technical Analysis | Perform the full engineering analysis of BAHX units - operating conditions, failure modes, inspection history, and risk ranking. | Kurt MacKay | Multiple | Completed | 1 | 2025-11-01 | 2026-03-15 | 2026-03-15 | Analysis complete. All BAHX units evaluated for operating envelope, failure risk, and inspection history. | 2026-03-15
T-007 | P-002 | BAHX Final Report | Compile the BAHX study into a formal engineering report documenting methodology, findings, and recommendations. | Kurt MacKay | N/A | In Progress | 1 | 2026-03-01 |  | 2026-04-15 | Report approximately 80% complete. Compiling final sections. |  | 2026-03-26
T-008 | P-002 | BAHX Presentation | Create a summary presentation to accompany the BAHX report for management and site teams. | Kurt MacKay | N/A | In Progress | 2 | 2026-03-20 |  | 2026-04-20 | Presentation started. Working in parallel with report finalization. |  | 2026-03-27
T-009 | P-002 | BAHX SOP Review | Review facility SOPs for BAHX units to identify any existing operational notes, restrictions, or cautions. | Kurt MacKay | Multiple | In Progress | 3 | 2026-03-15 |  | 2026-04-10 | Waiting on SOPs for BAHX units to review for any existing comments or operational notes. |  | 2026-03-25
T-010 | P-002 | BAHX Vendor Meeting - April 1 | Meet with BAHX vendor to learn about replacement unit cost, lead times, and available configurations. | Kurt MacKay | N/A | In Progress | 2 | 2026-03-20 |  | 2026-04-01 | Vendor meeting scheduled for April 1st. |  | 2026-03-26
T-011 | P-003 | Dashboard Development & Deployment | Build and deploy the Power BI corrosion coupon dashboard with all facility data. | Kurt MacKay | All | Completed | 2 | 2025-09-01 | 2026-03-15 | 2026-03-15 | Dashboard built, deployed, and in use. Historical data loaded. | 2026-03-15
T-012 | P-003 | Auto-Triggered Email Data Pipeline | Create an automated pipeline that ingests new corrosion coupon data from emailed reports and loads it into the dashboard. | Kurt MacKay | N/A | Not Started | 2 | 2026-04-01 |  | 2026-07-31 |  |  | 2026-03-29
T-013 | P-003 | Corrosion Dashboard Handoff Documentation | Create comprehensive documentation for the dashboard and pipeline to enable handoff to the next owner. | Kurt MacKay | N/A | Not Started | 3 | 2026-07-15 |  | 2026-08-31 |  |  | 2026-03-27
T-014 | P-004 | Inspection Scope Tool - Development | Build and deploy the tool that automates the creation of inspection scopes. | Kurt MacKay | N/A | Completed | 2 | 2025-06-01 | 2026-02-28 | 2026-02-28 | Tool is complete and currently in active use. | 2026-02-28
T-015 | P-004 | Inspection Scope Tool - Handoff Documentation | Create documentation so the tool can be maintained and used after handoff. | Kurt MacKay | N/A | Not Started | 3 | 2026-03-25 |  | 2026-04-30 |  |  | 2026-03-26
T-016 | P-005 | PI Vision Screen Cleanup - Units, Tags, and Navigation | Review and correct units, tag configuration, and navigation links on all 722 PI Vision screens. Low priority; worked on during downtime. | Dustin MacDonald | All | Ongoing | 5 |  |  |  | Very low priority. Worked on only during downtime. 722 screens total. |  | 2026-03-26
T-017 | P-006 | AI & Python Applications - Exploration & Prototyping | Evaluate AI and Python tools for SOP automation, PI data analysis, and general workflow improvements. | Self-Directed | N/A | Ongoing | 5 |  |  |  | Low priority, self-directed. Worked on during downtime. |  | 2026-03-25

## Deliverables
Deliverable ID | Task ID | Title | Description | Status | Start Date | End Date | Deadline | % Complete
D-001 | T-001 | Collect SDKs and P&IDs for all facilities | Gather Safety Data Knowledge packages and P&ID drawings for every facility in scope. | Completed | 2025-02-01 | 2025-03-15 | 2025-03-15 | 100
D-002 | T-001 | Define SCE identification methodology and criteria | Establish the criteria for classifying an element as safety-critical based on industry standards and AltaGas policies. | Completed | 2025-02-15 | 2025-03-30 | 2025-03-30 | 100
D-003 | T-001 | Complete SCE identification for well-documented facilities | Walk through P&IDs, identify all SCEs, and log each element per facility. | Completed | 2025-04-01 | 2025-12-31 | 2025-12-31 | 100
D-004 | T-001 | Build SCE master register for completed facilities | Compile all identified SCEs into a structured register with tag numbers, descriptions, and facility assignments. | Completed | 2025-10-01 | 2026-01-31 | 2026-01-31 | 100
D-005 | T-002 | Assess Harmattan SDK gaps - identify missing P&ID references | Catalog which tags in the Harmattan SDK lack P&ID cross-references and determine scope of the gap. | Completed | 2026-01-15 | 2026-02-15 | 2026-02-15 | 100
D-006 | T-002 | Assess EEEP SDK gaps - identify missing P&ID references | Catalog which tags in the EEEP SDK lack P&ID cross-references and determine scope of the gap. | Completed | 2026-02-01 | 2026-02-28 | 2026-02-28 | 100
D-007 | T-002 | Develop alternative mapping approach for tag-to-SCE identification | Create a methodology to identify SCEs at sites where SDKs do not map tags to P&IDs directly. | In Progress | 2026-02-15 |  | 2026-03-10 | 60
D-008 | T-002 | Complete SCE identification for Harmattan | Apply alternative mapping and complete the SCE register for Harmattan. | In Progress | 2026-03-10 |  | 2026-03-25 | 30
D-009 | T-002 | Complete SCE identification for EEEP | Apply alternative mapping and complete the SCE register for EEEP. | In Progress | 2026-03-15 |  | 2026-03-31 | 20
D-010 | T-003 | Export Maximo asset database for all facilities | Pull full asset lists from Maximo for every facility in scope. | Completed | 2025-10-01 | 2025-10-15 | 2025-10-15 | 100
D-011 | T-003 | Build tag matching logic and automated comparison | Create matching script/process to compare SCE tag numbers against Maximo records. | Completed | 2025-10-15 | 2025-11-15 | 2025-11-15 | 100
D-012 | T-003 | Run initial match - resolve easy hits (~45% matched) | Execute first matching pass; resolve tags with direct exact matches. | Completed | 2025-11-15 | 2026-02-28 | 2026-02-28 | 100
D-013 | T-003 | Investigate and resolve unmatched tags (~55% remaining) | Manually review remaining unmatched tags - naming discrepancies, missing Maximo entries, decommissioned equipment. | In Progress | 2026-03-01 |  | 2026-03-25 | 20
D-014 | T-003 | Produce final Maximo match report with gap summary | Document match rate, root causes of mismatches, and recommended Maximo updates. | Not Started | 2026-03-20 |  | 2026-03-31 | 0
D-015 | T-004 | Monitor PSGP-1 Dimsdale SDK validation progress | Track SDK validation status; confirm when validated SDK is available for SCE work. | On Hold | 2026-03-01 |  | 2026-05-15 | 0
D-016 | T-004 | Monitor Townsend SDK validation progress | Track SDK validation status for Townsend; confirm when validated SDK is ready. | On Hold | 2026-03-01 |  | 2026-05-15 | 0
D-017 | T-004 | Complete SCE identification for PSGP-1 Dimsdale | Once SDK is validated, perform full SCE identification using the confirmed P&IDs. | Not Started |  |  | 2026-06-15 | 0
D-018 | T-004 | Complete SCE identification for Townsend | Once SDK is validated, perform full SCE identification using the confirmed P&IDs. | Not Started |  |  | 2026-06-30 | 0
D-019 | T-005 | Prepare site-specific SCE summary packages | Create a per-facility SCE summary with tag lists, Maximo match rates, and gap analysis. | Not Started | 2026-04-01 |  | 2026-04-15 | 0
D-020 | T-005 | Schedule and conduct site review meetings | Coordinate with site leads to schedule and hold review meetings for all completed facilities. | Not Started | 2026-04-15 |  | 2026-06-15 | 0
D-021 | T-005 | Document action items and findings from site meetings | Capture feedback, corrective actions, and follow-up items from each site review. | Not Started | 2026-05-01 |  | 2026-06-30 | 0
D-022 | T-006 | Collect BAHX operating data and inspection records | Gather design datasheets, operating parameters, and historical inspection reports for all BAHX units. | Completed | 2025-11-01 | 2025-12-15 | 2025-12-15 | 100
D-023 | T-006 | Identify failure modes and risk factors | Evaluate common BAHX failure mechanisms (mercury embrittlement, thermal shock, fouling, corrosion) and apply to each unit. | Completed | 2025-12-15 | 2026-01-31 | 2026-01-31 | 100
D-024 | T-006 | Complete risk ranking of all BAHX units | Rank each BAHX unit by risk based on operating conditions, age, inspection findings, and failure mode applicability. | Completed | 2026-01-15 | 2026-02-28 | 2026-02-28 | 100
D-025 | T-006 | Finalize analysis conclusions and recommendations | Summarize findings and develop recommended actions for each unit. | Completed | 2026-02-28 | 2026-03-15 | 2026-03-15 | 100
D-026 | T-007 | Draft report - methodology, scope, and background | Write introductory sections covering the study scope, BAHX background, and methodology. | Completed | 2026-03-01 | 2026-03-10 | 2026-03-10 | 100
D-027 | T-007 | Draft report - analysis results and risk rankings | Write the core technical sections presenting per-unit findings and risk rankings. | Completed | 2026-03-10 | 2026-03-20 | 2026-03-20 | 100
D-028 | T-007 | Draft report - recommendations and action plan | Write the recommendations section with proposed inspection, monitoring, and replacement actions. | In Progress | 2026-03-20 |  | 2026-03-28 | 60
D-029 | T-007 | Incorporate vendor cost and lead-time data (post Apr 1 meeting) | After the April 1st vendor meeting, add replacement unit cost and lead-time info to the report. | Not Started | 2026-04-01 |  | 2026-04-07 | 0
D-030 | T-007 | Final review, formatting, and report submission | Proofread, format per AltaGas standards, and submit the final BAHX report. | Not Started | 2026-04-07 |  | 2026-04-15 | 0
D-031 | T-008 | Outline presentation structure and key messages | Define slide flow: background, methodology, key findings, risk rankings, recommendations. | In Progress | 2026-03-20 |  | 2026-03-25 | 50
D-032 | T-008 | Draft presentation slides | Build all slides with data, charts, and summary tables from the report. | Not Started | 2026-03-25 |  | 2026-04-10 | 0
D-033 | T-008 | Add vendor cost and lead-time slides (post Apr 1 meeting) | After the vendor meeting, add replacement cost and timeline slides. | Not Started | 2026-04-01 |  | 2026-04-12 | 0
D-034 | T-008 | Finalize and review presentation | Polish visuals, review with supervisor, and finalize for delivery. | Not Started | 2026-04-12 |  | 2026-04-20 | 0
D-035 | T-009 | Request SOPs for all BAHX-equipped facilities | Contact operations/document control to obtain current SOPs covering BAHX units. | Completed | 2026-03-15 | 2026-03-20 | 2026-03-20 | 100
D-036 | T-009 | Review SOPs for BAHX-related comments and restrictions | Read through received SOPs and extract any operational notes, startup/shutdown cautions, or maintenance remarks about BAHX units. | Not Started | 2026-03-25 |  | 2026-04-05 | 0
D-037 | T-009 | Incorporate SOP findings into BAHX report | Add any relevant SOP observations to the final report and recommendations. | Not Started | 2026-04-05 |  | 2026-04-10 | 0
D-038 | T-010 | Prepare BAHX unit specs and questions for vendor | Compile the specs of current BAHX units and prepare a list of questions about cost, lead time, and replacement options. | In Progress | 2026-03-20 |  | 2026-03-28 | 30
D-039 | T-010 | Attend vendor meeting and capture notes | Attend the April 1st meeting; record cost quotes, lead times, and configuration options. | Not Started | 2026-04-01 |  | 2026-04-01 | 0
D-040 | T-010 | Summarize vendor data into cost/lead-time table | Organize vendor quotes into a structured table for inclusion in the report and presentation. | Not Started | 2026-04-01 |  | 2026-04-04 | 0
D-041 | T-011 | Gather historical corrosion coupon data for all facilities | Collect and clean all available historical corrosion coupon measurement data. | Completed | 2025-09-01 | 2025-10-15 | 2025-10-15 | 100
D-042 | T-011 | Design and build Power BI data model | Create the data model, relationships, and DAX measures for corrosion tracking. | Completed | 2025-10-15 | 2025-11-30 | 2025-11-30 | 100
D-043 | T-011 | Build dashboard visuals and report pages | Create all report pages: facility overview, trend charts, coupon comparison, and alerts. | Completed | 2025-12-01 | 2026-01-31 | 2026-01-31 | 100
D-044 | T-011 | Deploy to Power BI Service and validate with stakeholders | Publish to the workspace, share with stakeholders, and incorporate feedback. | Completed | 2026-02-01 | 2026-03-15 | 2026-03-15 | 100
D-045 | T-012 | Define email ingestion requirements and data format | Document the email source, attachment format, field mapping, and expected cadence. | Not Started | 2026-04-01 |  | 2026-04-15 | 0
D-046 | T-012 | Build email-triggered Power Automate / Logic App flow | Create the automated flow that monitors the mailbox and triggers data extraction on new messages. | Not Started | 2026-04-15 |  | 2026-05-15 | 0
D-047 | T-012 | Build data transformation and loading step | Parse emailed data, clean and transform to match the Power BI data model, and load into the dataset. | Not Started | 2026-05-15 |  | 2026-06-15 | 0
D-048 | T-012 | End-to-end pipeline testing and error handling | Test the full pipeline with sample and live emails; add error notifications and retry logic. | Not Started | 2026-06-15 |  | 2026-07-15 | 0
D-049 | T-012 | Deploy pipeline to production | Promote the pipeline to production and confirm automatic data refresh is working. | Not Started | 2026-07-15 |  | 2026-07-31 | 0
D-050 | T-013 | Document data model, DAX measures, and data sources | Write technical docs covering the Power BI data model, all DAX formulas, and data source connections. | Not Started | 2026-07-15 |  | 2026-08-07 | 0
D-051 | T-013 | Document automated pipeline architecture and configuration | Write a guide covering the email pipeline: flow triggers, data transformations, error handling, and monitoring. | Not Started | 2026-08-01 |  | 2026-08-15 | 0
D-052 | T-013 | Create user guide for dashboard consumers | Write a guide for end-users explaining how to navigate the dashboard, interpret the visuals, and export data. | Not Started | 2026-08-10 |  | 2026-08-22 | 0
D-053 | T-013 | Conduct handoff walkthrough with successor | Walk through all documentation and systems live with the person taking over the dashboard. | Not Started | 2026-08-22 |  | 2026-08-31 | 0
D-054 | T-014 | Define inspection scope requirements and inputs | Identify all required inputs, logic, and output formats for generating inspection scopes. | Completed | 2025-06-01 | 2025-07-15 | 2025-07-15 | 100
D-055 | T-014 | Develop inspection scope generation logic | Implement the core logic to produce inspection scopes from input data. | Completed | 2025-07-15 | 2025-11-30 | 2025-11-30 | 100
D-056 | T-014 | Test and validate with real inspection data | Run the tool against real-world data and confirm output accuracy with engineering. | Completed | 2025-12-01 | 2026-01-31 | 2026-01-31 | 100
D-057 | T-014 | Deploy tool for active use | Package and deploy the tool so the team can use it in daily workflows. | Completed | 2026-02-01 | 2026-02-28 | 2026-02-28 | 100
D-058 | T-015 | Write technical documentation - code architecture and logic | Document the tool's code structure, key modules, and generation logic for future developers. | Not Started | 2026-03-25 |  | 2026-04-07 | 0
D-059 | T-015 | Write user guide - how to run the tool and interpret outputs | Create a step-by-step user guide covering inputs, execution, and output interpretation. | Not Started | 2026-04-07 |  | 2026-04-15 | 0
D-060 | T-015 | Document known limitations and future improvement ideas | List any known edge cases, limitations, and potential enhancements. | Not Started | 2026-04-15 |  | 2026-04-22 | 0
D-061 | T-015 | Conduct handoff walkthrough | Walk through the tool, documentation, and codebase with the designated successor. | Not Started | 2026-04-22 |  | 2026-04-30 | 0
D-062 | T-016 | Units cleanup - remove manual overrides, pull from PI tags | Remove manually typed display units and update each data link to pull units directly from the live PI tag configuration. | Ongoing |  |  |  | 5
D-063 | T-016 | Tag configuration review - flag misconfigured tags | Flag any tags requiring improved configuration (naming alignment, missing attributes, incorrect engineering units). | Ongoing |  |  |  | 5
D-064 | T-016 | Screen linking - add or correct navigation links | Add or correct navigation links between screens; reference PFDs to ensure asset relationships are accurate. | Ongoing |  |  |  | 5
D-065 | T-017 | Explore AI-assisted workflow opportunities | Identify use cases where AI or ML could improve engineering efficiency at AltaGas. | Ongoing |  |  |  | 20
D-066 | T-017 | Evaluate SOP automation feasibility | Assess whether AI can standardize or generate SOPs programmatically. | Ongoing |  |  |  | 10
D-067 | T-017 | Investigate ML models on PI data for operational insights | Prototype ML approaches for anomaly detection or optimization using PI historian data. | Ongoing |  |  |  | 5

## Timelines
Item ID | Item Type | Title | Parent ID | Start Date | Duration (days) | End Date | Deadline | Status | % Complete | Time Allocated | Time Spent | Scheduled Date | Milestones
P-001 | Project
P-002 | Project
P-003 | Project
P-004 | Project
P-005 | Project
P-006 | Project
T-001 | Task
T-002 | Task
T-003 | Task
T-004 | Task
T-005 | Task
T-006 | Task
T-007 | Task
T-008 | Task
T-009 | Task
T-010 | Task
T-011 | Task
T-012 | Task
T-013 | Task
T-014 | Task
T-015 | Task
T-016 | Task
T-017 | Task
D-001 | Deliverable
D-002 | Deliverable
D-003 | Deliverable
D-004 | Deliverable
D-005 | Deliverable
D-006 | Deliverable
D-007 | Deliverable
D-008 | Deliverable
D-009 | Deliverable
D-010 | Deliverable
D-011 | Deliverable
D-012 | Deliverable
D-013 | Deliverable
D-014 | Deliverable
D-015 | Deliverable
D-016 | Deliverable
D-017 | Deliverable
D-018 | Deliverable
D-019 | Deliverable
D-020 | Deliverable
D-021 | Deliverable
D-022 | Deliverable
D-023 | Deliverable
D-024 | Deliverable
D-025 | Deliverable
D-026 | Deliverable
D-027 | Deliverable
D-028 | Deliverable
D-029 | Deliverable
D-030 | Deliverable
D-031 | Deliverable
D-032 | Deliverable
D-033 | Deliverable
D-034 | Deliverable
D-035 | Deliverable
D-036 | Deliverable
D-037 | Deliverable
D-038 | Deliverable
D-039 | Deliverable
D-040 | Deliverable
D-041 | Deliverable
D-042 | Deliverable
D-043 | Deliverable
D-044 | Deliverable
D-045 | Deliverable
D-046 | Deliverable
D-047 | Deliverable
D-048 | Deliverable
D-049 | Deliverable
D-050 | Deliverable
D-051 | Deliverable
D-052 | Deliverable
D-053 | Deliverable
D-054 | Deliverable
D-055 | Deliverable
D-056 | Deliverable
D-057 | Deliverable
D-058 | Deliverable
D-059 | Deliverable
D-060 | Deliverable
D-061 | Deliverable
D-062 | Deliverable
D-063 | Deliverable
D-064 | Deliverable
D-065 | Deliverable
D-066 | Deliverable
D-067 | Deliverable

## Gantt Chart
Item ID | Title | Start | End | Status | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-27 | 2026-06-03 | 2026-06-10
P-001
P-002
P-003
P-004
P-005
P-006
T-001
T-002
T-003
T-004
T-005
T-006
T-007
T-008
T-009
T-010
T-011
T-012
T-013
T-014
T-015
T-016
T-017
D-001
D-002
D-003
D-004
D-005
D-006
D-007
D-008
D-009
D-010
D-011
D-012
D-013
D-014
D-015
D-016
D-017
D-018
D-019
D-020
D-021
D-022
D-023
D-024
D-025
D-026
D-027
D-028
D-029
D-030
D-031
D-032
D-033
D-034
D-035
D-036
D-037
D-038
D-039
D-040
D-041
D-042
D-043
D-044
D-045
D-046
D-047
D-048
D-049
D-050
D-051
D-052
D-053
D-054
D-055
D-056
D-057
D-058
D-059
D-060
D-061
D-062
D-063
D-064
D-065
D-066
D-067