## Overview
Weekly Status Report — March 19, 2026
Liam Vanhooren ¦ Engineering Co-op Student ¦ AltaGas Ltd.
Executive Summary
This reporting period, the active workload includes 2 high-priority project(s) actively progressing across AFS, Griffith; 1 medium-priority project(s) being completed with available time; 3 recurring weekly task(s); 4 background item(s) progressed opportunistically. No projects were closed this reporting period — current deliverables are multi-week efforts progressing through their respective milestones. 1 item(s) are in a Complete/Pending state awaiting further direction.
Site Support Distribution
Site | Active Tasks | % of Active | Completed (Historical) | % of Completed
AFS | 2 | 18% | 1 | 50%
All | 2 | 18% | 0 | 0%
Griffith | 1 | 9% | 1 | 50%
Harmattan | 1 | 9% | 0 | 0%
NP (North Pine) | 1 | 9% | 0 | 0%
Pipestone II | 2 | 18% | 0 | 0%
RIPET | 1 | 9% | 0 | 0%
Unassigned / Internal | 1 | 9% | 0 | 0%
Workload Priority Distribution
Priority Level | Count | % of Workload
P2 - High | 2 | 20%
P3 - Medium | 4 | 40%
P4 - Low | 1 | 10%
P5 - Background | 3 | 30%
Priority Spotlight — Top Active Work
P2 - High ¦ AFS PSV 7001 Replacement
Supervisor | Cameron Cooper
Site | AFS
Status | Ongoing
Commentary | I have managed a series of bids and found an appropriate PSV to replace PSV 7001. Kenneth and team ordered this Friday March 13. The PSV in question was not traditional and vendors could not provide a true replcement in kind on the timeline that operations required. Cameron approved the replacement, however he has also asked that moving forward I also attempt to complete PSV sizing for the valve. With a solution now in place, priority is moved from level 1 to level 2 as the operations constraint is resolved
P2 - High ¦ Griffith Butane Emissions Tracker – Scrubber & Well Shaft Additions
Supervisor | Cameron Cooper/Farzin Shokoohi
Site | Griffith
Status | Ongoing
Commentary | Well shaft blowdown calculations are complete — volume references extracted from existing vessel/pipe data and integrated successfully. Progress temporarily delayed while awaiting LSHH (High-High Level) height measurement for the compressor scrubber to finalize its blowdown volume. Followed up with operations, and LSHH height was provided today, allowing scrubber blowdown calculation to proceed. Next steps: finalize scrubber volume calculation, add it to the Volume Calcs tab, and create new line items on all monthly tabs.
P3 - Medium ¦ Create PSV Tags for Boiler PSVs (WO2057188)
Supervisor | Cameron Cooper
Site | AFS
Status | Ongoing
Commentary | Preparing to book a meeting with maintenance/engineering support (likely N. Luft or facility engineering contact) to confirm required tag format and scope.
Weekly Recurring Tasks
Title | Site | Status | Priority
RIPET / NP ESV Trial – Data Tracking & Reporting Setup | RIPET & NP (North Pine) | Not Started | P3 - Medium
Pipestone II – Sample Point Tag Mapping & Weekly TDE Data Refresh | Pipestone II | Ongoing | P3 - Medium
Weekly & Monthly MOC Reporting – Power BI, Excel, and PowerPoint Generation | All | Ongoing | P3 - Medium
Background & Lower Priority Work
Title | Supervisor | Site | Status | Priority
RFI Review & NCR Investigation Support | Mark Mcleod | Pipestone II | Ongoing | P4 - Low
Harmattan C3 Booster Study – Report Update & Follow-Up Discussion | Jordy Flemming | Harmattan | Ongoing | P5 - Background
PI Vision Screen Cleanup – Units, Tag Configuration, and Navigation Links | Dustin MacDonald | All | Ongoing | P5 - Background
AI & Python Applications for Workflow Automation and Operational Optimization | Self‑Directed (Personal Development Initiative) | N/A | Ongoing | P5 - Background
Complete / Pending — Awaiting Further Direction
These items have reached a deliverable milestone but remain open pending follow-up scope or re-activation.
Title | Supervisor | Site | Status Commentary | Priority
PSM Roadmap Upcoming Continuation and Support | Charles Vincent | RIPET (with possible expansion to other facilities) | Received email indicating potential next steps: supporting MOC close‑out tracking across additional facilities. Current deliverables are completed. Pending further direction and anticipated involve | P5 - Background
Recently Completed Projects (Past Week)
No projects were completed since last Monday. Current project timelines extend beyond a single reporting period.
Deliverables Completed — Last 30 Days
No projects have been formally completed in the last 30 days. Active work items are longer-duration efforts with deliverables expected in upcoming reporting periods.
Work Assigned by Supervisor
Supervisor | Active Assignments | % of Workload
Cameron Cooper | 2 | 20%
Dustin MacDonald | 2 | 20%
Cameron Cooper/Farzin Shokoohi | 1 | 10%
Jordy Flemming | 1 | 10%
Mark Mcleod | 1 | 10%
Self‑Directed (Personal Development Initiative) | 1 | 10%
Steve Kingdom | 1 | 10%
Loni Van der lee | 1 | 10%
Looking Ahead
Heading into next week, primary focus will remain on "AFS PSV 7001 Replacement", "Griffith Butane Emissions Tracker – Scrubber & Well Shaft Additions", "Create PSV Tags for Boiler PSVs (WO2057188)". Lower-priority items will be advanced as capacity allows.

## Weekly Work
Title | Supervisor | Site | Required Deliverables | Project Description | Status Commentary | Status | Priority
RIPET / NP ESV Trial – Data Tracking & Reporting Setup | Steve Kingdom | RIPET & NP (North Pine) | Set up Excel‑based tracking system for Emergency Shutoff Valve (ESV) trial performance sheets. Receive daily paper copies from RIPET and NP operators and transcribe into master Excel tracker. Maintain shared file location for trial data (either shared RIPET folder or NP‑specific location, pending facility direction). Support consistency between trial forms, test sheets, and commissioning plan documents. Provide accurate, up‑to‑date weekly metrics to the engineering team. | Engineering is launching a four‑week Emergency Shutoff Valve (ESV) trial at both RIPET and NP. Shift supervisors at each facility will complete performance sheets for every railcar connection to evaluate ESV performance, operational timing, leak frequency, and overall workflow impacts. My role will be to maintain the master tracking file, compile trial metrics, and ensure clean data consolidation from both sites. Current files in place are sample placeholders; the actual facility‑completed sheets will be integrated once received. This task is expected to transition into an ongoing weekly responsibility throughout the duration of the trial. | Current file package includes sample forms only (Trial Performance Sheet, Test Plan, Commissioning Plan). Actual submissions from RIPET/NP are pending. Awaiting confirmation from facilities on: Whether NP will use the same shared SharePoint file or require a separate file location. Which operators/supervisors will be responsible for uploading or scanning their paper forms. Preparing to support daily/weekly data entry once reporting workflow is defined. | Not Started | 3
Pipestone II – Sample Point Tag Mapping & Weekly TDE Data Refresh | Loni Van der lee | Pipestone II | Compile and maintain a complete list of facility sample points, mapped to PI tags. Provide weekly refreshed data extracts to TDE using PI Datalink. Investigate and resolve (or categorize) unmapped sample points. Maintain documentation of mapping logic and data‑quality notes for TDE. Support development of a future automated process if required. | To support TDE’s ongoing analytics for Pipestone II, a full dataset of sample points and associated PI tags was required. This involved manually reviewing ~20 drawing packages to compile all instrumented sample points and then mapping each point to its corresponding PI tag where available. This dataset now feeds TDE’s weekly analysis, requiring recurring updates pulled from PI Datalink. Additional investigation is ongoing to understand why some sample points remain unmapped—initial observations suggest these points do not have corresponding PI tags configured in the system. | Completed manual extraction of sample point lists from ~20 drawing packages and mapped them to PI tags. Delivered initial dataset to TDE and confirmed that the structure aligns with their analytic workflow. Began weekly refresh process using PI Datalink; current workflow is lengthy due to manual tag queries and re‑alignment of output data. Identified a subset of sample points with no associated PI tags; confirmed that this appears to be a configuration gap rather than a mapping error. Exploring options for cleanup, including: Flagging orphaned sample points for facility instrumentation review, Creating placeholder entries or exclusion rules in the dataset, Potentially requesting tag creation if required by analytics. Will continue providing weekly data refreshes until TDE’s final model stabilizes or an automation path is approved. | Ongoing | 3
Weekly & Monthly MOC Reporting – Power BI, Excel, and PowerPoint Generation | Dustin MacDonald | All | Weekly MOC report (Excel + PowerPoint) submitted every Monday by 10 AM. Monthly MOC report including stacked bar charts, quarter trends, month‑over‑month metrics, and Pending / >1‑year reports. Maintain dated folders and SharePoint uploads per the required process. Communicate completion to reporting distribution list. | This is a recurring reporting responsibility that supports MOC governance across the organization. The weekly report is generated from the Power BI “MOC All‑Time Stats” tab and requires exporting filtered data, updating the Excel template (Calcs sheet), and embedding results into the PowerPoint template. [MOC Report...t Up Guide ¦ Word] The monthly report is more extensive and requires refreshing the Power BI Desktop version of the report (45+ minute refresh) followed by multiple exports, graph updates, 3D map refresh inside Excel, manual data pasting, and formatting for several additional reporting sections. [MOC Report...t Up Guide ¦ Word] This task ensures leadership receives accurate, up‑to‑date visibility into MOC activity, performance ratios, backlog, and compliance tracking. | Completed weekly MOC reporting as required. Weekly process is straightforward and now well‑practiced. Monthly reporting remains a multi‑hour, high‑effort task due to: Required refresh of Power BI Desktop (~45 minutes) Multiple exported datasets (Counts by Month, Change in Period, Pending Approvals, Approved >1 Year, etc.) Manual updates to Excel Calcs, 3D map, and PowerPoint quarter reporting slides Formatting and data validation per the Set‑Up Guide workflow | Ongoing | 3

## Ongoing Projects
Title | Project Supervisor | Site | Required Deliverables | Project Description | Status Commentary | Status | Priority
AFS PSV 7001 Replacement | Cameron Cooper | AFS | Identify and source viable replacements for a non‑standard, hard‑to‑procure PSV. Present multiple technically acceptable options for engineering review. Provide full due‑diligence checks (capacity, set pressure, inlet sizing, backpressure limits, CRN, service suitability). Document the engineering delegation and technical validation in a formal record. [PSV_Replac...REGO_3131G ¦ Word] Support operations in procuring the selected replacement. Scope follow‑up task: complete full PSV sizing and basis‑of‑design verification when time allows. | A field PSV urgently required replacement, but the original OMECA EU‑19 model was non‑standard and extremely difficult to source, especially on short notice. My role was to rapidly identify suitable alternatives and verify technical equivalency under guidance from the responsible professional engineer. I located the REGO 3131G valve as one of several potential replacement candidates—despite it being a specialty LPG valve not widely stocked—and confirmed it met the required relieving capacity, inlet size, service rating, and CRN applicability. [PSV_Replac...REGO_3131G ¦ Word] I then prepared the due‑diligence and delegation document to capture engineering approval, technical checks, and installation considerations so operations could proceed confidently. | I have managed a series of bids and found an appropriate PSV to replace PSV 7001. Kenneth and team ordered this Friday March 13. The PSV in question was not traditional and vendors could not provide a true replcement in kind on the timeline that operations required. Cameron approved the replacement, however he has also asked that moving forward I also attempt to complete PSV sizing for the valve. With a solution now in place, priority is moved from level 1 to level 2 as the operations constraint is resolved | Ongoing | 2
Create PSV Tags for Boiler PSVs (WO2057188) | Cameron Cooper | AFS | Verification of existing PSV locations inside the boiler Development of correct PSV tag naming/numbering Updated tagging scheme consistent with site standards Marked-up P&IDs showing revised PSV tags Submission of updated tagging information to Maximo/CMMS | This task involves replacing generic labels “PSV 1” and “PSV 2” currently used for the boiler's internal PSVs with proper tag numbers aligned with site engineering standards and equipment hierarchy. Work includes confirming PSV specifications, identifying the correct tag format, updating documentation, and ensuring operations and maintenance teams have clear, traceable identifiers for the relief devices. | Preparing to book a meeting with maintenance/engineering support (likely N. Luft or facility engineering contact) to confirm required tag format and scope. | Ongoing | 3
Griffith Butane Emissions Tracker – Scrubber & Well Shaft Additions | Cameron Cooper/Farzin Shokoohi | Griffith | Add gas compressor scrubber blowdowns to the butane emissions workbook (similar to propane sheet). Add product well shaft blowdowns for pump/motor retrieval. Validate or generate volume calculations for new blowdown items. Update Volume Calcs tab with correct pipe lengths/diameters or vessel volumes. Ensure the new items feed through to all monthly tabs and the Summary tab. Provide updated spreadsheet back to operations (Kevin Watson). | Operations requested updates to the Griffith butane emissions tracking spreadsheet to improve accounting of product losses to flare. The current tracker excludes two key sources: (1) compressor scrubber vapor releases, and (2) product well shaft blowdowns performed during pump/motor workovers. These additions will align butane tracking with the propane workbook and improve emissions and product loss accuracy. | Well shaft blowdown calculations are complete — volume references extracted from existing vessel/pipe data and integrated successfully. Progress temporarily delayed while awaiting LSHH (High-High Level) height measurement for the compressor scrubber to finalize its blowdown volume. Followed up with operations, and LSHH height was provided today, allowing scrubber blowdown calculation to proceed. Next steps: finalize scrubber volume calculation, add it to the Volume Calcs tab, and create new line items on all monthly tabs. | Ongoing | 2
Harmattan C3 Booster Study – Report Update & Follow-Up Discussion | Jordy Flemming | Harmattan | Update original booster study into AltaGas’ standard report template. Clean, reorganize, and polish technical content for archival use. Document operational discussion points regarding propane egress and costream-to-raw conversion potential. Provide summary of limitations and dependencies (other bottlenecks, pump constraints, pipeline behavior). | This work relates to a previously completed engineering study evaluating propane flow‑boosting options on the Harmattan‑to‑Didsbury C3 pipeline. The original report assessed booster pumps at multiple locations and the impact on propane egress and raw gas processing capability. As a low priority task, the original draft is being updated to match AltaGas’ standard reporting format and improve readability. This refresh also includes capturing the earlier discussions with Jordy regarding how increased propane egress could theoretically allow a shift of inlet volumes from costream to raw gas. However, the team recognized that without assessing the next set of infrastructure bottlenecks, conclusions regarding actual capability increases cannot yet be supported. | Work has been deprioritized for both Jordy and myself due to higher‑priority operational tasks. Identified that no meaningful conclusions can be drawn until a proper bottleneck investigation is completed (downstream equipment, fractionation limits, inlet compressors, etc.). Report update will remain a background task, progressed intermittently as time permits. | Ongoing | 5
RFI Review & NCR Investigation Support | Mark Mcleod | Pipestone II | Participate in RFI review process with Mark to understand workflow, documentation, and expected outputs. | While awaiting information for other active projects, I began shadowing Mark on an RFI to gain familiarity with AltaGas’ RFI workflow, approval stages, and documentation standards. The issue under review may escalate to a Non‑Conformance Report (NCR) depending on the quantified impact and supporting data. My involvement is expected to increase as the investigation develops and may include preparing engineering justification, assembling evidence, and contributing to the draft NCR package. | Shadowed Mark to understand the RFI process, including routing, required documentation, and the review sequence. Gained visibility into issue background and the evidence required if reclassification to NCR is pursued. Current direction is trending toward issuing an NCR, pending quantification of data to support non‑conformance. A meeting is already scheduled for next week to discuss findings and next steps, and to determine my expected involvement. Will assist with data analysis and documentation once technical details and required thresholds are clarified. | Ongoing | 4
PSM Roadmap Upcoming Continuation and Support | Charles Vincent | RIPET (with possible expansion to other facilities) | Develop automated tooling and logic to identify, classify, and organize formal and anecdotal MOCs at RIPET. Scrape folder structures (2019–2021, legacy folders) to extract and categorize MOCs. [altagas-my...epoint.com] Cross‑reference folder‑derived MOCs against master lists (RIPET Master List, Old MOC Log). [altagas-my...epoint.com] Generate structured CSV outputs for engineering/operations review. Prepare a comprehensive inventory of outstanding MOCs to support RIPET PSI readiness. | This project involved creating a robust, automated workflow to identify, classify, and validate MOCs at the RIPET facility by parsing folders, documents, and historical logs. The work produced a complete picture of formal and anecdotal MOCs, their PSI impacts, and their readiness for closure—supporting the broader PSM Roadmap 2026 initiative. [altagas-my...epoint.com] After completing this phase, I received direction that the scope may expand beyond RIPET, with leadership expressing interest in consistent tracking of MOC close‑outs across other sites. In particular, I was highlighted as a resource due to the quality of the RIPET work. | Received email indicating potential next steps: supporting MOC close‑out tracking across additional facilities. Current deliverables are completed. Pending further direction and anticipated involvement Priority expected to increase as scope expands | Complete/Pending | 5
PI Vision Screen Cleanup – Units, Tag Configuration, and Navigation Links | Dustin MacDonald | All | For each PI Vision screen (722 total), review and correct: Units Cleanup – Remove manually typed display units and update each data link to pull units directly from the live PI tag configuration. Tag Configuration Review – Flag any tags requiring improved configuration (naming alignment, missing attributes, incorrect engineering units). Screen Linking – Add or correct navigation links between screens; requires referencing PFDs to ensure flows and asset relationships are accurate. | This is a long‑term, background cleanup effort intended to improve PI Vision usability and pave the way for future enterprise‑wide PI screen standardization. Current PI screens contain numerous inconsistencies as they were originally built without consistent practices, requiring detailed manual review of every visible data link on every screen. Work is completed only during downtime between higher‑priority tasks. This aligns with the broader initiative highlighted by Dustin and added to Aaron’s PI Vision working list, targeting gaps and missing links across multiple facilities. [altagas-my...epoint.com] | This task remains very low priority and is worked on only when other project deliverables are awaiting inputs. The total cleanup scope is 722 screens, each requiring multiple individual corrections. Work is tedious due to significant inconsistencies in the original screen design. Completed 25 screens yesterday, using available downtime while waiting on higher‑priority details. Identified multiple recurring issues including manual unit overrides, inconsistent link structures, and tags lacking proper configuration. Will continue progressing opportunistically. | Ongoing | 5
AI & Python Applications for Workflow Automation and Operational Optimization | Self‑Directed (Personal Development Initiative) | N/A | Explore opportunities to use Python, machine learning, and AI‑assisted workflows to improve engineering efficiency. Evaluate feasibility of automating SOP standardization/document‑generation workflows. Investigate ML approaches for optimizing operations or improving insights derived from PI data. Document findings, constraints, and potential future implementations. | This is a personal, low‑priority innovation initiative focused on using AI and Python to streamline engineering workflows and operational analysis. The initial concept explored leveraging AI models to automatically standardize or generate SOPs, reducing manual drafting time. However, this effort encountered technical and cost‑related challenges, as meaningful implementation would require programmatic access to AI APIs integrated into Python workflows—far beyond the free GitHub Copilot‑level assistants currently available to the team. The next phase will focus on evaluating whether Python‑based machine learning models applied to PI data can provide value in areas such as predictive insights, operations optimization, and anomaly detection. | Planning to begin exploratory notebooks and model prototyping during downtime between higher‑priority tasks. This remains a low‑priority, self‑directed initiative but may support future digital transformation goals. | Ongoing | 5

## Completed Projects
Title | Supervisor | Site | Required Deliverables | Project Description | Status Commentary | Status | Priority | Date Completed
PSV 1251/1201 Degassing duplicate label issue | Cameron Cooper | AFS | Complete Red line and appropriate updates to fix the double‑label PSV issue for degassing Pots for Daryn Staudt. |  | I found a newer revision of the drawing that Daryn requested redlining for this week. The double lebeled PSV issue is resolved. | Completed | 2
Butane Cavern PSV Leak – Product Loss & Emissions Estimate | Cameron Cooper/Farzin Shokoohi | Griffith | Engineering estimate of butane product lost to flare during PSV failure. Aspen HYSYS depressurization model setup & execution. Summary report including assumptions, model basis, and quantified loss. Communication of results to operations for emissions and inventory reconciliation. | A PSV on the Griffith butane cavern failed between Dec 12–15, 2025, leaking vapor to flare until discovery. Operations requested a ballpark estimate of product lost. Using observed cavern pressure drop (0.5 psi) and two‑phase thermodynamic equilibrium modeling, the analysis estimated the equivalent mass of liquid butane lost as vapor during the relief event. | Reviewed request from operations regarding PSV venting that filled the 1000‑gallon flare knockout drum and caused multi-day product release. [altagas-my...epoint.com] Developed Aspen HYSYS model replicating the cavern’s initial equilibrium state (20.1 psig, 123,600 bbl liquid inventory). [Griffith B...- 01152026 ¦ Word] Performed dynamic depressurization simulation to match the observed 0.5 psi pressure decline. Calculated total equivalent butane loss as 327 barrels of liquid product. [Griffith B...- 01152026 ¦ Word] Documented assumptions including negligible trucking contribution, equilibrium vapor–liquid behavior, and conservative treatment of full pressure drop being attributed to PSV leak. Final report prepared and issued (Rev A, Jan 22, 2026). [Griffith B...- 01152026 ¦ Word] Results emailed back to operations for emissions reporting and inventory reconciliation. | Completed | 2

## Sheet4
I am putting together a weekly work tracking report to help share how my time is being split to my boss dustin. The columns are as follows: Title Supervisor Site Required Deliverables Project Description Status Commentary Status Priority - I am going to share files from items in my work and I want you to help come up with descriptions etc. and even some commentary - the commentary is like what actions I have taken.