## Overview
Weekly Dashboard — April 13, 2026
Dev Tester ¦ Developer ¦ _TestCompany
Project Status Summary
Project | Category | Status | Priority | Active Tasks | % Complete | Allocated (hrs) | Spent (hrs)
Weekly Site Operations | Weekly | In Progress | P1 – Urgent | 2 | 0/2 | 4.0 | 1.5
Compressor Station Upgrade | Ongoing | In Progress | P1 – Urgent | 3 | 0/3 | 12.0 | 3.5
SCADA System Migration | Ongoing | In Progress | P2 – High | 2 | 1/2 | 13.0 | 11.0
Weekly Schedule
Priority | Mon 04/13 | Tue 04/14 | Wed 04/15 | Thu 04/16 | Fri 04/17 | Sat 04/18 | Sun 04/19
P1 – Urgent | Complete safety audit checklist Commission new VFD units
P2 – High |  | Build Ignition overview screens for South Site | Run control wiring for Phase 2
P3 – Medium |  |  |  | Update project tracking spreadsheet Update PLC program for new VFDs
P4 – Low |  |  |  | Configure historian for South Site tags
P5 – Background
Time Overview
Project | Allocated (hrs) | Spent (hrs) | Remaining (hrs) | Utilization %
Weekly Site Operations | 4.0 | 1.5 | 2.5 | 38%
Compressor Station Upgrade | 12.0 | 3.5 | 8.5 | 29%
SCADA System Migration | 13.0 | 11.0 | 2.0 | 85%
TOTAL | 29.0 | 16.0 | 13.0 | 55%
Upcoming Deadlines (Next 14 Days)
Deadline | Item | Status | Parent
2026-04-15 | Follow up with electrical vendor | On Hold | Weekly Site Operations
2026-04-15 | OPC tag mapping spreadsheet | In Progress | Build Ignition overview screens for South Site
2026-04-17 | Update project tracking spreadsheet | Not Started | Weekly Site Operations
2026-04-18 | Complete safety audit checklist | In Progress | Weekly Site Operations
2026-04-18 | Safety audit report | In Progress | Complete safety audit checklist
2026-04-18 | Photo documentation log | Not Started | Complete safety audit checklist
2026-04-20 | Cable pull schedule | In Progress | Run control wiring for Phase 2

## Projects
Project ID | Title | Category | Supervisor | Site | Description | Status | Priority | Start Date | End Date | Deadline | Date Completed | Notes
P-001 | Weekly Site Operations | Weekly | Jane Smith | North Plant | Routine weekly operational tasks across all sites. | In Progress | 2 | 2026-03-01 |  |  |  | Primary weekly workload — reviewed every Monday.
P-002 | Compressor Station Upgrade | Ongoing | Bob Martinez | South Site | Multi-phase upgrade of the south site compressor station — new VFDs and control wiring. | In Progress | 1 | 2026-03-15 | 2026-06-30 | 2026-06-30 |  | Budget approved Q1. Phase 1 VFD install complete. Phase 2 wiring in progress.
P-003 | SCADA System Migration | Ongoing | Jane Smith | All Sites | Migrate legacy SCADA displays from FactoryTalk to Ignition platform. | In Progress | 2 | 2026-02-01 | 2026-09-30 | 2026-09-30 |  | Phase 1 (North Plant) complete. Phase 2 (South Site) in progress. Phase 3 (East Facility) planned Q3.
P-004 | Operator Training Documentation | Completed | Bob Martinez | North Plant | Create training materials for new control systems. | Completed | 3 | 2026-02-01 | 2026-03-28 | 2026-04-01 | 2026-03-28 | All training delivered. Positive ops feedback received.

## Tasks
Task ID | Project ID | Title | Description | Supervisor | Site | Status | Priority | Start Date | End Date | Deadline | Status Commentary | Date Completed | Scheduled Date
T-001 | P-001 | Complete safety audit checklist | Walk through all safety checkpoints in the north plant control room. | Jane Smith | North Plant | In Progress | 1 | 2026-04-13 | 2026-04-18 | 2026-04-18 | Started Monday — two sections remaining. |  | 2026-04-13
T-002 | P-001 | Update project tracking spreadsheet | Refresh hours, status, and notes for all active tasks. | Jane Smith | North Plant | Not Started | 3 | 2026-04-14 | 2026-04-17 | 2026-04-17 |  |  | 2026-04-16
T-003 | P-001 | Follow up with electrical vendor | Email vendor about delayed panel delivery and get revised ETA. | Jane Smith | North Plant | On Hold | 2 | 2026-04-13 | 2026-04-15 | 2026-04-15 | Vendor out of office until Wednesday — will follow up Thursday.
T-004 | P-002 | Commission new VFD units | Power up, configure parameters, and verify operation of 3x VFD units. | Bob Martinez | South Site | In Progress | 1 | 2026-04-01 | 2026-05-01 | 2026-05-01 | Unit 1 commissioned. Units 2 and 3 scheduled this week. |  | 2026-04-13
T-005 | P-002 | Run control wiring for Phase 2 | Pull cable, terminate, and label all control wiring between VFD room and MCC. | Bob Martinez | South Site | Not Started | 2 | 2026-04-15 | 2026-05-30 | 2026-05-30 | Waiting on cable tray install — expected by April 15. |  | 2026-04-15
T-006 | P-002 | Update PLC program for new VFDs | Add Modbus comms blocks and interlock logic for 3 new VFD drives. | Bob Martinez | South Site | Not Started | 3 | 2026-04-20 | 2026-05-15 | 2026-05-15 |  |  | 2026-04-16
T-007 | P-003 | Build Ignition overview screens for South Site | Recreate the 12 main process overview screens in Ignition Perspective. | Jane Smith | South Site | In Progress | 2 | 2026-03-15 | 2026-05-30 | 2026-05-30 | 8 of 12 screens recreated. Remaining 4 are alarm summary and trending pages. |  | 2026-04-14
T-008 | P-003 | Configure historian for South Site tags | Set up tag history in Ignition for all critical process variables. | Jane Smith | South Site | Not Started | 4 | 2026-05-01 | 2026-06-15 | 2026-06-15 | Blocked until tag mapping is finalized. |  | 2026-04-16
T-009 | P-004 | Write standard operating procedures | Draft and review SOPs for the 5 new control system processes. | Bob Martinez | North Plant | Completed | 2 | 2026-02-01 | 2026-03-14 | 2026-03-15 | All 5 SOPs approved and filed. | 2026-03-14
T-010 | P-004 | Deliver operator training sessions | Conduct 3 training sessions (2 hours each) for day and night shift operators. | Bob Martinez | North Plant | Completed | 2 | 2026-03-17 | 2026-03-28 | 2026-03-28 | All 3 sessions delivered. Attendance sheets filed. | 2026-03-28

## Deliverables
Deliverable ID | Task ID | Title | Description | Status | Start Date | End Date | Deadline | % Complete | Time Allocated | Time Spent
D-001 | T-001 | Safety audit report | PDF report summarizing all findings and corrective actions. | In Progress | 2026-04-13 | 2026-04-17 | 2026-04-18 | 40 | 3 | 1.5
D-002 | T-001 | Photo documentation log | Timestamped photos of each inspection point. | Not Started | 2026-04-14 | 2026-04-17 | 2026-04-18 | 0 | 1 | 0
D-003 | T-004 | VFD commissioning record | Test results and parameter settings for each unit. | In Progress | 2026-04-01 | 2026-04-28 | 2026-05-01 | 33 | 6 | 2
D-004 | T-005 | As-built wiring diagram | Updated single-line and wiring diagrams reflecting actual field installation. | Not Started |  |  | 2026-05-30 | 0 | 4 | 0
D-005 | T-005 | Cable pull schedule | List of all cables with from/to, length, and pull date. | In Progress | 2026-04-13 | 2026-04-20 | 2026-04-20 | 60 | 2 | 1.5
D-006 | T-007 | Screen design mockups | PDF mockups of all 12 overview screens approved by operations. | Completed | 2026-03-15 | 2026-04-01 | 2026-04-01 | 100 | 8 | 7.5
D-007 | T-007 | OPC tag mapping spreadsheet | Mapping from old FactoryTalk tags to new Ignition OPC paths. | In Progress | 2026-04-01 | 2026-04-15 | 2026-04-15 | 75 | 5 | 3.5
D-008 | T-009 | Printed SOP binder | Laminated and bound set of all 5 SOPs for the control room. | Completed | 2026-03-10 | 2026-03-14 | 2026-03-15 | 100 | 3 | 2.5
D-009 | T-010 | Training presentation slides | PowerPoint deck covering system overview, alarms, and emergency procedures. | Completed | 2026-03-10 | 2026-03-16 | 2026-03-17 | 100 | 4 | 4.5
D-010 | T-010 | Attendance and quiz records | Sign-in sheets and quiz results for all 3 sessions. | Completed | 2026-03-17 | 2026-03-28 | 2026-03-28 | 100 | 1 | 1

## Timelines
Item ID | Item Type | Title | Parent ID | Start Date | Duration (days) | End Date | Deadline | Status | % Complete | Time Allocated | Time Spent | Scheduled Date | Milestones
P-001 | Project
P-002 | Project
P-003 | Project
P-004 | Project
T-001 | Task
T-002 | Task
T-003 | Task
T-004 | Task
T-005 | Task
T-006 | Task
T-007 | Task
T-008 | Task
T-009 | Task
T-010 | Task
D-001 | Deliverable
D-002 | Deliverable
D-003 | Deliverable
D-004 | Deliverable
D-005 | Deliverable
D-006 | Deliverable
D-007 | Deliverable
D-008 | Deliverable
D-009 | Deliverable
D-010 | Deliverable

## Gantt Chart
Item ID | Title | Start | End | Status | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
P-001
P-002
P-003
P-004
T-001
T-002
T-003
T-004
T-005
T-006
T-007
T-008
T-009
T-010
D-001
D-002
D-003
D-005
D-006
D-007
D-008
D-009
D-010
No Scheduled Start
D-004